## Project Planner
Capstone Project Planner
Actual Start
Week-ending on:
[7 empty] | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-07 | 2022-01-09 | 2022-01-16 | 2022-01-13 | 2022-01-14 | 2022-01-15 | 2022-01-16
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | OWNER | % COMPLETE | Project Week#
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  | 47 | 48 | 49 | 50
Kick start - Introduction call with Team | 1 | 1 | 1 | 1 | All | 100%
Identifying ownership for Project Tasks | 1 | 1 | 1 | 1 | All | 100%
Git Repository & Access setup | 1 | 3 | 1 | 2 | Indra | 100%
Documentation - Interim Report | 2 | 3 |  |  | Manju | 0%
Interim Report - Team peer review | 3 | 1 |  |  | All | 0%
Interim Report - Walkthrough with Project Guide | 3 | 2 |  |  | Manju | 0%
Interim Report submission | 4 | 1 |  |  | Manju | 0%
Project Development/Testing | 2 | 5 |  |  | All | 0%
Explorartory Data Analysis | 2 | 3 |  |  | Sunil | 0%
Model Building | 3 | 4 |  |  | All | 0%
Performance Evaluation | 4 | 3 |  |  | All | 0%
Hyper Parameter tuning | 5 | 2 |  |  | All | 0%
Project review with Project Guide & feedback | 6 | 2 |  |  | All | 0%
Project submission | 7 | 1 |  |  | TBC | 0%
Documentation - Final Report | 2 | 5 |  |  | Manju | 0%
Final Report - Team peer review | 5 | 2 |  |  | All | 0%
Final Report - Walkthrough with Project Guide | 5 | 2 |  |  | TBC | 0%
Final Report submission | 7 | 1 |  |  | TBC | 0%