## Project Planner
Capstone Project Planner
[8 empty] | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Calendar Day
 | time axis 2021-11-28 to 2022-01-16
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | OWNER | % COMPLETE | 2021-11-28: Project Day #
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Kick start - Introduction call with Team | 1 | 1 | 1 | 1 | All | 100%
Identifying ownership for Project Tasks | 1 | 1 | 1 | 1 | All | 100%
Git Repository & Access setup | 1 | 3 | 1 | 2 | Indra | 100%
Documentation - Interim Report | 3 | 14 |  |  | TBC | 0%
Interim Report - Team peer review | 14 | 3 |  |  | All | 0%
Interim Report - Walkthrough with Project Guide | 17 | 6 |  |  | Manju | 0%
Interim Report submission | 22 | 1 |  |  | Manju | 0%
Project Development/Testing | 2 | 34 |  |  | All | 0%
Explorartory Data Analysis | 2 | 7 |  |  | Sunil | 0%
Model Building | 9 | 7 |  |  | All | 0%
Performance Evaluation | 16 | 7 |  |  | All | 0%
Hyper Parameter tuning | 23 | 7 |  |  | All | 0%
Project review with Project Guide & feedback | 30 | 7 |  |  | All | 0%
Project submission | 41 | 1 |  |  | TBC | 0%
Documentation - Final Report | 16 | 26 |  |  | Manju | 0%
Final Report - Team peer review | 30 | 7 |  |  | All | 0%
Final Report - Walkthrough with Project Guide | 36 | 6 |  |  | TBC | 0%
Final Report submission | 41 | 1 |  |  | TBC | 0%